## Module Controlling
Module |  | Module Name | [5 empty] | Module Manager | [11 empty] | Name
Overall Status |  |  | Green |  |  | Achievements since last report |  |  | Planned next steps | [12 empty] | Risks, Obstacles, Decisions needed
Degree of completion |  |  | 22.5% |  |  | Text |  |  | Text | [12 empty] | Text
Date of report |  |  | 2021-11-22
Planned End of workstream |  |  | 2022-03-13
Forecast End of workstream |  |  | 2022-03-20
Delay (weeks) |  |  | 0
 | time axis 2021-07-12 to 2022-11-07
# | Deliverables |  | Responsible | Completion | PLAN Start | PLAN End | FC END | Effort
D1 | … |  | Name | 90% | 2021-07-12 | 2021-07-20 | 2021-08-03 | High
D2 |  |  | Name | 80% | 2021-07-20 | 2021-07-27 | 2021-08-03 | Low
D3 |  |  | Name | 70% | 2021-07-27 | 2021-08-17 | 2021-08-24 | Low
D4 |  |  | Name | 60% | 2021-08-17 | 2021-08-24 | 2021-08-31 | Medium
D5 |  |  | Name | 50% | 2021-08-24 | 2021-08-31 | 2021-09-07 | Medium
D6 |  |  | Name | 40% | 2021-08-31 | 2021-09-07 | 2021-09-14 | Medium
D7 |  |  | Name | 30% | 2021-09-07 | 2021-09-14 | 2021-09-21 | Medium
D8 |  |  | Name | 20% | 2021-09-14 | 2021-09-21 | 2021-09-28 | Medium
D9 |  |  | Name | 10% | 2021-09-21 | 2021-10-31 | 2021-11-30 | Medium
D10 |  |  | Name | 0% | 2021-10-31 | 2021-11-07 | 2021-11-14 | Medium
D11 |  |  | Name | 0% | 2021-11-07 | 2021-11-14 | 2021-11-21 | Medium
D12 |  |  | Name | 0% | 2021-11-14 | 2021-12-24 | 2021-12-31 | Medium
D13 |  |  | Name | 0% | 2021-12-24 | 2021-12-31 | 2022-01-07 | Medium
D14 |  |  | Name | 0% | 2021-12-31 | 2022-01-07 | 2022-01-14 | High
D15 |  |  | Name | 0% | 2022-01-07 | 2022-01-14 | 2022-01-21 | Medium
D16 |  |  | Name | 0% | 2022-01-14 | 2022-02-13 | 2022-02-20 | Medium
D17 |  |  | Name | 0% | 2022-02-13 | 2022-02-20 | 2022-02-27 | Medium
D18 |  |  | Name | 0% | 2022-02-20 | 2022-02-27 | 2022-03-06 | Medium
D19 |  |  | Name | 0% | 2022-02-27 | 2022-03-06 | 2022-03-13 | Medium
D20 |  |  | Name | 0% | 2022-03-06 | 2022-03-13 | 2022-03-20 | Medium
Formulas:
FC END = +[Achievements since last report]+14
Achievements since last report = +[PLAN Start]+7
PLAN Start = +[Achievements since last report, row above]